# Greater Minnesota

# Transportation Alternatives Program

2026/2027 Solicitation Guidebook

This guidebook has been modified for use by applicants within the Northeast Minnesota Area Transportation Partnership (NEMNATP). This includes applicants from Aitkin, Carlton, Cook, Itasca, Koochiching, Lake, Pine, and St. Louis Counties. This also includes Metropolitan Interstate Council (DSMIC) Planning Area Applicants

Funding in year 2031

Table of Contents

Table of Contents	2

Overview	3

Funding Availability	3

Related Documents	3

Transportation Alternatives Solicitation Information	4

Federal Program Requirements	4

Qualifying Activities	4

Non-Qualifying Activities	5

Project Sponsors and Applicants	6

Sponsors	6

Applicants	6

Local Match and Cost Sharing Requirements	7

Timeline Guidance for Project Development to Construction	8

RDO & MPO Contact Information	9

Regional Development Organization Contact Information	10

Metropolitan Planning Organization Contact Information	11

ATP Contact Information	12

Area Transportation Partnership Contact Information	13

Other Key Contacts	14

Statewide Transportation Alternatives Contact Information	14

Safe Routes to School, Scenic Byway & Recreational Trails Program Coordinator Contact Information	14

# Overview

For the 2026/2027 application cycle, area transportation partnerships (ATPs) are conducting solicitations for Transportation Alternatives (TA) projects. This document explains the overall solicitation process and the eligibility requirements for TA funding.

## Funding Availability

The 2026/2027 TA solicitation includes funding being made available in Fiscal Year (FY) 2031. Funding target estimates are provided below.

| Fiscal Year | Funding Target Estimate* |
| --- | --- |
| 2031 | $1.5-1.8 Million |

*Please Note: As of the solicitation announcement (October 5, 2026), Federal funding targets are still in draft. The estimate above is consistent with prior fiscal year authorizations. Finalized funding targets will be communicated to applicants and sponsors at our earliest convenience.

Applicants are also encouraged to review eligibility and activity guidelines for the Carbon Reduction Program (CRP). For more information about, please visit WEBSITE or contact ARDC Senior Planner, Travis Houle (thoule@ardc.org)

# 2026/27 Solicitation Timeline

Monday, Oct. 5, 2026 – Announce solicitation; Open LOI period

Friday, Oct. 31, 2026 – Deadline for applicants to submit LOI

Monday, Dec. 1, 2026 – Official start of full application period

Friday, Jan. 8, 2027 – Deadline for applicants to submit full applications

- NOTE: Application Deadline has been corrected above. Applications are due by 1/8/27

All applicants will receive a notification with the results of the selection process no later than March 30, 2027.

# Related Documents

TA Solicitation Letter of Intent – starting for the 2026/2027 application cycle, ATPs will handle Letters of Intent (LOIs) directly. Full information about creating and submitting an LOI are available from each ATP directly.

TA Solicitation Full Application – the full application form for the TA solicitation. Full application documents are available from each ATP directly.

  - Note: The NEMNATP will release the formal application at the conclusion of our LOI review period.

# Transportation Alternatives Solicitation Information

## Federal Program Requirements

Following is a partial listing of the regulations that apply to any project receiving federal transportation funds. These requirements must be taken into consideration for budget development, project development and project implementation stages.

Davis-Bacon and Copeland Acts: Payment of pre-determined wage is applicable to all federal-aid construction contracts exceeding $2,000 and to all related subcontracts.

ADA Requirements: All TA projects must comply with the federal and state accessibility mandates. For additional information contact State Aid for Local Transportation.

Anti-Discrimination Laws: Each sponsoring participant must comply with applicable federal and state Anti-discrimination laws and be able to demonstrate compliance.

Project Supervision: All projects must be under the direct supervision of a Minnesota Licensed Professional Engineer.

Additional Requirements and Specifications: Successful applicants will be provided with additional information as needed by Minnesota Department of Transportation (MnDOT).

## Qualifying Activities

As identified in federal law, TA funds may be obligated for projects or activities described in 23 U.S.C. 101(a)(29) or 213, as such provisions were in effect on the day before the date of enactment of the FAST Act.

Former 23 U.S.C. 213(b)(1):

- TA as defined in section 101 [former 23 U.S.C. 101(a)(29)]:
The term “Transportation Alternatives” means any of the following activities when carried out as part of any program or project authorized or funded under this title, or as an independent program or project related to surface transportation:

  - Construction, planning, and design of on-road and off-road trail facilities for pedestrians, bicyclists, and other non-motorized forms of transportation, including sidewalks, bicycle infrastructure, pedestrian and bicycle signals, traffic calming techniques, lighting and other safety-related infrastructure, and transportation projects to achieve compliance with the Americans with Disabilities Act of 1990 (42 U.S.C. 12101 et seq.).

  - Construction, planning, and design of infrastructure-related projects and systems that will provide safe routes for non-drivers, including children, older adults, and individuals with disabilities to access daily needs.

  - Conversion and use of abandoned railroad corridors for trails for pedestrians, bicyclists, or other non-motorized transportation users.

  - Construction of turnouts, overlooks, and viewing areas.

  - Community improvement activities, which include but are not limited to:

    - inventory, control, or removal of outdoor advertising;

    - historic preservation and rehabilitation of historic transportation facilities;

    - vegetation management practices in transportation rights-of-way to improve roadway safety, prevent against invasive species, and provide erosion control; and

    - archaeological activities relating to impacts from implementation of a transportation project eligible under title 23.

  - Any environmental mitigation activity, including pollution prevention and pollution abatement activities and mitigation to:

    - address stormwater management, control, and water pollution prevention or abatement related to highway construction or due to highway runoff, including activities described in sections 23 U.S.C. 133(b)(3) [as amended under the FAST Act], 328(a), and 329 of title 23; or

    - reduce vehicle-caused wildlife mortality or to restore and maintain connectivity among terrestrial or aquatic habitats (Former 23 U.S.C. 213(b)(2)-(4)).

- The recreational trails program under 23 U.S.C. 206 of title 23.

- The scenic byways program under U.S.C. 162 of title 23.

- The safe routes to school program eligible projects and activities listed at section 1404(f) of the SAFETEA-LU:

  - Infrastructure-related projects.

  - Non-infrastructure-related activities.

  - SRTS coordinator. SAFETEA-LU section 1404(f)(2)(A) lists “managers of safe routes to school programs” as eligible under the non-`infrastructure projects.

- Planning, designing, or constructing boulevards and other roadways largely in the right-of-way of former Interstate System routes or other divided highways.

  - See Boulevards from Divided Highways for examples.

There are no location restrictions for TA set-aside infrastructure projects; they are not required to be located along highways.

For SRTS non-infrastructure projects, traffic education and enforcement activities must take place within approximately two miles of a primary or middle school (kindergarten through 8th grade).

## Non-Qualifying Activities

As identified in federal law, TA funds cannot be used for the following activities because there is no authorization under the Federal-aid Highway Program:

State or metropolitan planning organization administrative purposes. Exceptions:

  - See FHWA’s Memo Allocating Indirect Costs to Projects, dated September 4, 2015.

  - RTP administrative costs of the State for RTP set-aside funds.

Promotional activities, except as permitted under the SRTS (2 CFR 200.421(e)(3)).

Routine maintenance and operations, except trail maintenance as permitted under the RTP.

General recreation and park facilities, playground equipment, sports fields, campgrounds, picnic areas and pavilions, etc.

MnDOT has elected that the following activities are also considered ineligible for TA funding, even if not prohibited federally.

Engineering activities

Purchase of right-of-way

## Project Sponsors and Applicants

### Sponsors

Federal funds for TA projects are passed through MnDOT to recipients that are adequately staffed and equipped to undertake and satisfactorily complete the requirements associated with federally-funded work.   MnDOT determined that state aid cities (i.e. cities with population of over 5,000 persons) and counties are qualified recipients for federal funds. The TA solicitation requires their participation as a sponsor and/or applicant.  If an eligible applicant is not a state aid city or county, then the applicant will need a state aid city or county to be a sponsor on their project.  For a full description of state aid sponsor requirements please review the state aid manual.

### Applicants

Project applicants must be an entity eligible to receive federal TA funding. Eligible applicants are:

- a local government: Local government entities include any unit of local government below a State government agency, except for an MPO. Examples include city, town, township, or county agencies.

- a regional transportation authority: Regional transportation authorities are considered the same as the Regional Transportation Planning Organizations defined in the statewide planning section (23 U.S.C. 135(m)).

- a transit agency: Transit agencies include any agency responsible for public transportation that is eligible for funds as determined by the Federal Transit Administration.

- a natural resource or public land agency: Natural resource or public land agencies include any Federal, Tribal, State, or local agency responsible for natural resources or public land administration. Examples include:

  - State or local park or forest agencies;

  - State or local fish and game or wildlife agencies;

  - Department of the Interior Land Management Agencies; and

  - U.S. Forest Service.

- a school district, local education agency, or school: School districts, local education agencies, or schools may include any public or nonprofit private school. Projects should benefit the general public and not only a private entity.

- a tribal government.

- a nonprofit entity responsible for the administration of local transportation safety programs: Examples include a nonprofit entity responsible for:

  - a local program implementing construction, planning, and design of infrastructure-related projects and systems that will provide safe routes for non-drivers, including children, older adults, and individuals with disabilities to access daily needs; and

  - a safe routes to school program.

- any other local or regional governmental entity with responsibility for, or oversight of, transportation or recreational trails (other than an MPO or a State agency) that the State determines to be eligible, consistent with the goals of this subsection.

State DOTs and MPOs are not eligible entities as defined under 23 U.S.C. 133(h)(4)(B) and therefore are not eligible project sponsors for TA funds. However, State DOTs and MPOs may partner with an eligible entity project sponsor to carry out a project.

Nonprofit organizations are not eligible as direct grant subrecipients for TA funds unless they qualify through one of the eligible entity categories (e.g., where a nonprofit organization is a designated transit agency, school, or an entity responsible for the administration of local transportation safety programs). Nonprofit entities are eligible to partner with any eligible entity on an eligible project, if State or local requirements permit.

Tribal governments need to be federally recognized to be eligible entities for TA funding. If a tribal government is not a federally recognized tribe, the tribe does not possess certain inherent rights of self-government and are not entitled to receive federal benefits, services and protections.

The Recreational Trails Program set-aside funds retain the RTP eligible project sponsor provisions under 23 U.S.C. 206 (23 U.S.C. 133(h)(5)(C)).

## Local Match and Cost Sharing Requirements

For all projects, including SRTS projects, funded with TA funds, the federal share is the same as for the general federal-aid highway program: 80 percent Federal and 20 percent State or local match subject to the sliding scale adjustment. (23 U.S.C. 120)

As provided in 49 CFR 18.24 "Matching or cost sharing," the following requirements are emphasized:

18.24(b) Qualifications and exceptions-(1) Costs borne by other Federal grant agreements. Except as provided by Federal statute, a cost sharing or matching requirement may not be met by costs borne by another Federal grant. This prohibition does not apply to income earned by a grantee or subgrantee from a contract awarded under another Federal grant.

(3) Cost or contributions counted towards other Federal costs-sharing requirements. Neither costs nor the values of third-party in-kind contributions may count towards satisfying a cost sharing or matching requirement of a grant agreement if they have been or will be counted towards satisfying a cost sharing or matching requirement of another Federal grant agreement, a Federal procurement contract, or any other award of Federal funds.

## Timeline Guidance for Project Development to Construction

| Time from funding award | Activity and duration |
| --- | --- |
| 7-13 months | Eligible agency completes planning and preliminary work to describe and estimate cost of project. (26-52 weeks but public input and collaboration with landowners may take longer) |
| 13-20 months | Project is selected in four-year State Transportation Improvement Program. (26 weeks) |
| 20-33 months | Eligible agency completes preliminary engineering to assess social, environmental and economic impacts and to apply design criteria. (26-52 weeks) |
| 20-33 months | Preliminary discussions and review scoping as to appropriate document. (2 weeks) |
| 21-36 months | Eligible agency prepares environmental document. (4-13 weeks) |
| 23-38 months | Eligible agency submits environmental documentation to District State Aid Engineer with original signatures. (6-8 weeks) |
| 24-40 months | District State Aid Engineer reviews the documents. Are document components appropriate / correct? If no, eligible agency is contacted to resolve. Eligible agency corrects and resubmits. (Add 6-8 weeks if second draft is needed) |
| 26-43 months | District State Aid Engineer reviews; comments and/or approves. (8-10 weeks) |
| 26-43 months | State Aid for Local Transportation notifies District State Aid Engineer and eligible agency of environmental clearance approval and to proceed with right of way, detailed plans and necessary documentation for federal authorization. (1-2 weeks) |
| 32-50 months | Eligible agency completes and submits plans, right of way certification and required documentation to the District State Aid Engineer. (13-26 weeks) |
| 35-52 months | Plan review by District State Aid Engineer and State Aid for Local Transportation. (10 weeks) |
| 36-54 months | Federal authorization to let project. (5 weeks) |
| 36-54 months | Bid opening and certification of Disadvantaged Business Enterprises. (2 weeks) |
| 37-55 months | Contractor secures bond and signs contract. (2 weeks) |
| 38-55 months | Contract approval and initiation of construction. (3 weeks) |

## RDO & MPO Contact Information

The Metropolitan Planning Organizations (MPO) and Regional Development Organizations (RDO) are key partners in the TA solicitation process being responsible for reviewing projects to determine success in the TA program. Any local community applicant who has questions about the application process and is interested in submitting a proposal are encouraged to connect with an RDO or MPO. Contact information may be found on the following pages where project specific questions, eligibility requirements and scoring criteria may be directed.

### Regional Development Organization Contact Information

| Region | Organization name | Counties served | Address & phone | Website |
| --- | --- | --- | --- | --- |
| 1 | Northwest Regional Development Commission | Kittson, Marshall, Norman, Pennington, Polk, Red Lake, Roseau | 109 S Minnesota St Warren, MN 56762 218-745-9107 | www.nwrdc.org |
| 2 | Headwaters Regional Development Commission | Beltrami, Clearwater, Hubbard, Lake of the Woods, Mahnomen | 403 4th St NW PO Box 906 Bemidji, MN 56601 218-444-4732 | www.hrdc.org |
| 3 | Arrowhead Regional Development Commission | Aitkin, Carlton, Cook, Itasca, Koochiching, Lake, St. Louis | 221 West 1st St Duluth, MN 55802 218-722-5545 | www.ardc.org |
| 4 | West Central Initiative | Becker, Clay, Douglas, Grant, Otter Tail, Pope, Stevens, Traverse, Wilkin | 1000 Western Ave PO Box 318 Fergus Falls, MN 56538 218-739-2239 | www.wcif.org |
| 5 | Region 5 Development Commission | Cass, Crow Wing, Morrison, Todd, Wadena | 200 1st Street NE Suite 2 Staples, MN 56479 218-894-3233 | www.regionfive.org |
| 6e | Mid-Minnesota Development Commission | Kandiyohi, McLeod, Meeker, Renville | 333 SW 6th St Suite 2 Willmar, MN 56201 320-235-8504 | www.mmrdc.org |
| 6w | Upper Minnesota Valley Regional Development Commission | Big Stone, Chippewa, Lac qui Parle, Swift, Yellow Medicine | 323 W Schlieman Ave Appleton, MN 56208 320-289-1981 | www.umvrdc.org |
| 7e | East Central Regional Development Commission | Chisago, Isanti, Kanabec, Mille Lacs, Pine | 100 S Park St Mora, MN 55051 320-679-4065 | http://www.ecrdc.org/ |
| 7W | Administered by MnDOT District 3 | Benton, Sherburne, Stearns and Wright | 7694 Industrial Park Road Baxter, MN 56425 218-828-5700 | www.dot.state.mn.us/d3/atp |
| 8 | Southwest Regional Development Commission | Cottonwood, Jackson, Lincoln, Lyon, Murray, Nobles, Pipestone, Redwood, Rock | 2401 Broadway Ave Suite 1 Slayton, MN 56172 507-836-8547 | www.swrdc.org |
| 9 | Region 9 Development Commission | Blue Earth, Brown, Faribault, Le Sueur, Martin, Nicollet, Sibley, Waseca, Watonwan | 3 Civic Center Plaza Suite 310 Mankato, MN 56001 507-387-5643 | www.rndc.org |
| 10 | Administered by MnDOT District 6 | Rice, Goodhue, Wabasha, Steele, Dodge, Olmsted, Winona, Freeborn, Mower, Fillmore, Houston | 2900 48th Street NW Rochester, MN 55901 507-286-7500 | www.dot.state.mn.us/d6/atp |

### Metropolitan Planning Organization Contact Information

| Organization name | Address & phone | Website |
| --- | --- | --- |
| Rochester-Olmstead Council of Governments | 2122 Campus Drive SE Suite 100 Rochester, MN 55904 507-328-7100 | www.co.olmsted.mn.us |
| Mankato-North Mankato Area Planning Organization | 10 Civic Center Plaza Mankato, MN 56001 507-387-8613 | www.mnmapo.org |
| St. Cloud Area Planning Organization | 1040 County Road 4 St. Cloud, MN 56303 320-252-7568 | www.stcloudapo.org |
| Fargo-Moorhead Metropolitan Council of Governments | 1 2nd Street N Suite 232 Fargo, ND 58102 701-232-3242 | www.fmmetrocog.org |
| Duluth-Superior Metropolitan Interstate Council | 221 W 1st Street Duluth MN 218-529-7509 | www.dsmic.org |
| La Crosse Area Planning Committee | 212 6th Street N Room 1200 La Crosse, WI 54601 608-785-5977 | www.lacrossecounty.org/metropolitan-planning-organization/LAPC-Home |
| Grand Forks-East Grand Forks Metropolitan Planning Organization | 255 N 4th Street Grand Forks, ND 58206 701-746-2660 | www.theforksmpo.org |
| Twin Cities Metropolitan Council | 390 Robert Street N St. Paul, MN 55101 651-602-1000 | www.metrocouncil.org |

## ATP Contact Information

### Area Transportation Partnership Contact Information

| ATP | Counties served | Address & phone | Website |
| --- | --- | --- | --- |
| 1 | Aitkin, Carlton, Cook, Itasca, Koochiching, Lake, Pine, St. Louis | 221 West 1st St Duluth, MN 55802 218-722-5545 | www.nemnatp.org |
| 2 | Beltrami, Clearwater, Hubbard, Kittson, Lake of the Woods, Marshall, Norman, Pennington, Polk, Red Lake, Roseau | MnDOT District 2 3920 Highway 2 West Bemidji, MN 56601 218-755-6500 | www.dot.state.mn.us/d2/atp |
| 3 | Benton, Cass, Crow Wing, Isanti, Kanabec, Mille Lacs, Morrison, Sherburne, Stearns, Todd, Wadena, Wright | MnDOT District 3 7694 Industrial Park Road Baxter, MN 56425 218-828-5700 | www.dot.state.mn.us/d3/atp |
| 4 | Becker, Big Stone, Clay, Douglas, Grant, Mahnomen, Otter Tail, Pope, Stevens, Swift, Traverse, Wilkin | MnDOT District 4 1000 Highway 10 West Detroit Lakes, MN 56501 218-846-3600 | www.dot.state.mn.us/d4/atp |
| Metro | Anoka, Carver, Chisago, Dakota, Hennepin, Ramsey, Scott, Washington | MnDOT Metro District 1500 West Co Rd B-2 Roseville, MN 55113 651-234-7500 | www.dot.state.mn.us/metro |
| 6 | Dodge, Fillmore, Freeborn, Goodhue, Houston, Mower, Olmsted, Rice, Steele, Wabasha, Winona | MnDOT District 6 2900 48th Street NW Rochester, MN 55901 507-286-7500 | www.dot.state.mn.us/d6/atp |
| 7 | Blue Earth, Brown, Cottonwood, Faribault, Jackson, LeSueur, Martin, Nicollet, Nobles, Rock, Sibley, Waseca, Watonwan | MnDOT District 7 2151 Bassett Drive Mankato, MN 56001 507-304-6100 | www.dot.state.mn.us/d7/atp |
| 8 | Chippewa, Kandiyohi, Lac qui Parle, Lincoln, Lyon, McLeod, Meeker, Murray, Pipestone, Redwood, Renville, Yellow Medicine | MnDOT District 8 2505 Transportation Road Willmar, MN 56201 320-231-5195 | www.dot.state.mn.us/d8/atp |

Note: Chisago County submits a Greater Minnesota TA application because it is not part of the seven-county Twin Cities metropolitan area, even though it is part of the Metro ATP. Chisago county TA applications are reviewed and scored by the East Central Regional Development Commission before they are forwarded to the Metro ATP integration committee.

## Other Key Contacts

### Statewide Transportation Alternatives Contact Information

| Name | Role | Address & Phone | Email |
| --- | --- | --- | --- |
| Noah Hansen | MnDOT Capital Planning Coordinator | 395 John Ireland Blvd MS 440 St. Paul, MN 55155 651-366-3742 | Noah.Hansen@state.mn.us |

### Safe Routes to School, Scenic Byway & Recreational Trails Program Coordinator Contact Information

| Name | Role | Address & Phone | Email |
| --- | --- | --- | --- |
| Kelly Corbin | MnDOT Safe Routes to School Non-Infrastructure Coordinator | 395 John Ireland Blvd MS 315 St. Paul, MN 55155 507-286-7590 | Kelly.Corbin@state.mn.us |
| Steve Prusak | MnDOT Safe Routes to School Engineering Coordinator | 395 John Ireland Blvd MS 500 St. Paul, MN 55155 651-366-3827 | Steven.Prusak@state.mn.us |
| Tim Wilcox | MnDOT Scenic Byway Coordinator | 395 John Ireland Blvd MS 620 St. Paul, MN 55155 612-449-0754 | Tim.Wilcox@state.mn.us |
| Dan Golner | MnDNR Recreational Trails Coordinator | 500 Lafayette Road Box 39 Saint Paul, MN 55155 651-259-5599 | Daniel.Golner@state.mn.us |